## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 2 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | WEEK
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Specification | 1 | 2 | 1 | 2 | 100%
Progress Report | 6 | 3 | 6 | 3 | 0% | bar: WEEK 15 to WEEK 20
Presentation Preparation | 16 | 3 | 16 | 3 | 0%
Final Report | 3 | 19 | 3 | 19 | 0%
Researching Axelrod's model | 1 | 5 | 1 | 5 | 40%
Network Generation | 3 | 4 | 3 | 4 | 0% | bar: WEEK 15 to WEEK 20
Creating UI | 5 | 3 | 5 | 3 | 0%
Simulating Axelrod's model | 6 | 4 | 6 | 4 | 0%
Testing different topologies | 9 | 4 | 9 | 4 | 0%
Introducing Forgiveness | 12 | 4 | 12 | 4 | 0%
Testing | 16 | 3 | 16 | 3 | 0%
Overflow time | 19 | 3 | 19 | 3 | 0%